## thanks , can u help me with agi
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 (Sep 22 - Oct 01) | Sprint 1 | M1-1 | As a developer, I need the database schema designed and implemented (User, Flight, Booking tables). | Must Have | None | Intern | Done
Sprint 1 (Sep 22 - Oct 01) | Sprint 1 | M1-2 | As a system, I need sample flight data populated with city/country names and constraints. | Must Have | M1-1 | Intern | Done
Sprint 2 (Oct 02 - Oct 15) | Sprint 2 | M2-1 | As a user, I want to search and retrieve all flights via API for filtering. | Must Have | M1-1 | Intern | Done
Sprint 2 (Oct 02 - Oct 15) | Sprint 2 | M2-3 | As a system, I need to implement dynamic pricing logic (seats, demand, time factors). | Must Have | M2-1 | Intern | Done
Sprint 2 (Oct 02 - Oct 15) | Sprint 2 | M2-6 | As a system, I need a background job (APScheduler) to simulate demand fluctuations. | Should Have | M2-3 | Intern | Done
Sprint 2 (Oct 02 - Oct 15) | Sprint 2 | M2-4 | As a user, I want an autocomplete dropdown for selecting origin and destination airports. | Should Have | M2-1 | Intern | Done
Sprint 3 (Oct 16 - Oct 27) | Sprint 3 | M3-1 | As a user, I want a Reserve → Pay multi-step workflow to hold a seat before payment. | Must Have | M2-3 | Intern | Done
Sprint 3 (Oct 16 - Oct 27) | Sprint 3 | M3-2 | As a system, I must use database transactions to confirm payment and decrement the seat atomically. | Critical | M3-1 | Intern | Done
Sprint 3 (Oct 16 - Oct 27) | Sprint 3 | M3-4 | As a user, I want to view my transaction history and download a personalized PDF ticket. | Must Have | M3-2 | Intern | Done
Sprint 3 (Oct 16 - Oct 27) | Sprint 3 | M3-5 | As a user, I want to cancel a ticket (with partial refund) and view the cancellation history via audit log. | Should Have | M3-2 | Intern | Done