## thanks , can u help me with agi
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Intern | 2025-10-05 | KeyError: 'demand_factor' when fetching flights after initial DB setup. | Sprint 2 | Intern | Integration | Added demand_factor column via ALTER TABLE to resolve schema mismatch. | 2025-10-05 | Closed | Resolved DB/code mismatch.
2 | Intern | 2025-10-18 | AttributeError: 'NoneType' object has no attribute 'get' in cancellation/history section. | Sprint 3 | Intern | Runtime | Added if cancel_result: check to safely handle None return from API helper. | 2025-10-18 | Closed | Resolved Frontend null pointer crash.
3 | Intern | 2025-10-23 | Transaction History Not Showing due to incorrect user_id being used (hardcoded ID=1 instead of logged-in user's ID). | Sprint 3 | Intern | Data Logic | Updated BookingRequest Pydantic model and create_booking function to use request.user_id. | 2025-10-23 | Closed | Resolved Critical History Mismatch.
4 | Intern | 2025-10-26 | Frontend Price Serialization Crash (ArrowInvalid) on displaying DataFrames containing formatted currency ($X.XX). | Sprint 3 | Intern | Compatibility | Applied .astype(str) conversion to currency columns in display_flights_data and history module to enforce string type for PyArrow. | 2025-10-26 | Closed | Resolved Streamlit data type incompatibility.